## Sheet1
Week | <component>
2020-10-01 | Team introduction / Environment Assement
2020-10-08 | Scope of work /Requirements finalized
2020-10-15 | Development Phase 1 + Pipelne creation
2020-10-22 | Development Phase 2 + Pipeline integration
2020-10-29 | Development Phase 3 + pipeline deployment
2020-11-05 | Deployment + Testing
2020-11-12 | Deployment + Testing
2020-11-19 | Dev Release
2020-11-26 | Staging Release
2020-12-03 | Prod Release
2020-12-10 | Bug Fix
2020-12-17 | Go Live
| Goals | Goals
| Cloud shell Integration with Git Hub | Azure Setup
| MakeFile | Setup Azure Pipelines
| Virtual Environment | Build Azure Pipeline
| Test Code | Run ML Service
| Build Server | Alert creation

## Sheet2
To | Doing | Done
Cloud shell Integration with Git Hub
| Setup Azure Pipelines | Azure Setup
Virtual Environment | Build Azure Pipeline | MakeFile
Python Pip | Run ML Service
Test Code | Alert creation
Build Server

## Sheet3
| Development | Microservice development | Testing | Deployment
Week 1 | Python code | ML
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8