## Sheet1
Week | <component> | Release
2020-10-01 | Team introduction / Environment Assement
2020-10-08 | Scope of work /Requirements finalized
2020-10-15 | Development Phase 1 + Pipelne creation
2020-10-22 | Development Phase 2 + Pipeline integration
2020-10-29 | Development Phase 3 + pipeline deployment
2020-11-05 | Deployment + Testing
2020-11-12 | Deployment + Testing
2020-11-19 | Dev Release
2020-11-26 | Staging Release
2020-12-03 | Prod Release
2020-12-10 | Bug Fix
2020-12-17 | Go Live
| Top Goals | Prioritized Features | Propose Difficulty | Featured Category | Project Management Guidelines | Cloud shell Integration with Git Hub | Azure Setup
[6 empty] | MakeFile | Setup Azure Pipelines
| Connect Azure to GItHub | connect to GitHub Repo | 1 | Create a github repo and connect to Azure | Demo Every Monday | Virtual Environment | Build Azure Pipeline
| Continous Integration | Setup Azure Cloudshell | 2 | use cloudshell to make the files | Weekly planning after demo | Test Code | Run ML Service
| Continous Delivery | Deploy using Azure Pipeline | 3 | Use an app service to deply a pipeline for continous delivery | Stakeholder release every 2 weeks | Build Server | Alert creation
| Mult environment | Deploy in staging environment |  | complete end to end application deployment , testing

## Sheet2
To | Doing | Done
Cloud shell Integration with Git Hub
| Setup Azure Pipelines | Azure Setup
Virtual Environment | Build Azure Pipeline | MakeFile
Python Pip | Run ML Service
Test Code | Alert creation
Build Server

## Sheet3
| Development | Microservice development | Testing | Deployment
Week 1 | Python code | ML
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8